## Feuil1
solution 1 package 3 roads 2 tenders
year | comments | 2012 |  |  |  |  | 2013 | [51 empty] | 2014 | [51 empty] | 2015
month |  | November | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  |  | July
week |  | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
start date of Consultancy Contract EGIS | 30 month end 22 Nov | November 48: 2012-11-23
kick off meeting | 27th December 2012 | November 48: 2012-11-27
collection of data | bar: December 49
preliminary meeting | 5 th December 2012 | bar: December 49
inception report | bar: December 51
reception of the Design | bar: December 52; February 9
Design check | bar: January 2 to January 5; February 9 to March 13
Design report | bar: February 6; March 13
modification Design | bar: February 6 to February 9
tender preparation | bar: February 9 to March 13
Bank no objection | bar: April 14 to April 16
Quaterly report n°1 | bar: April 14
Tender procedure | bar: April 17 to June 23
Tender evaluation | bar: June 24 to July 27
Bank no objection | bar: July 28 to July 30
Quaterly report 2 | bar: July 27
signature of the Contrat | bar: July 31 to August 34
Work Contract start date | bar: August 35
Commencement date | bar: September 39
Works | bar: September 39 to September 38
Winter period | bar: November 48 to March 11
defect liability period | bar: September 39 to July 28
Quaterly report 3 | bar: September 36
reception of the Design | bar: July 28
Design check | bar: July 28 to July 29
Quaterly report 4
Design report | bar: July 29
modification Design | bar: July 30
tender preparation | bar: July 31
Bank no objection | bar: August 32 to August 33
Tender procedure | bar: August 34 to September 39
Tender evaluation | bar: October 40 to October 43
Bank no objection | bar: October 44 to November 45
signature of the Contrat | bar: November 46 to December 49
Work Contract start date | bar: December 50
Commencement date | bar: January 1
Works | bar: January 2 to December 52
Winter period | bar: November 48 to March 11; November 48 to March 11
defect liability period | bar: January 1 to July 32
preparation TD1 | 8 month | bar: December 49 to August 32
defect liability period TD1 | 10 months | bar: August 33 to July 32
preparation TD2 | 6 months | bar: July 28 to January 1
defect liability period TD2 | 5 months | bar: January 1 to July 32